## IF Breakdown (hidden)
Level | Step | Predecessor
0 | 1
1 | 1.1
2 | 1.1.1
2 | 1.1.2
2 | 1.1.3
3 | 1.1.3.1 |  |  | Supports up to 99 sub-steps within a parent step
3 | 1.1.3.2
3 | 1.1.3.3 |  | Status | Description
2 | 1.1.4 |  | done | if any level and greater than above
2 | 1.1.5 |  | done | if greater than level 2 and lower than above
3 | 1.1.5.1 |  | done | if two and less than above
3 | 1.1.5.2 |  | done | if two and same as above
4 | 1.1.5.2.1 |  | done | if two and greater than above
2 | 1.1.6 |  | done | if one and same as above
1 | 1.2 |  | done | if one and less than above
2 | 1.2.1
3 | 1.2.1.1
4 | 1.2.1.1.1
5 | 1.2.1.1.1.1
6 | 1.2.1.1.1.1.1
5 | 1.2.1.1.1.2
4 | 1.2.1.1.2
3 | 1.2.1.2
3 | 1.2.1.3
2 | 1.2.2
2 | 1.2.3
2 | 1.2.4
3 | 1.2.4.1
2 | 1.2.5
1 | 1.3
1 | 1.4
1 | 1.5
1 | 1.6

## Work Breakdown Structure
| Project Inputs |  |  |  | Template Work Breakdown Structure | [5 empty] | Project Completion
|  | 16.67% | [8 empty] | 16.67%
| Project Name: |  | Template
| Project Manager(s) |  | Bob Saget, Rick Astley |  | Project Managers: Bob Saget, Rick Astley | [5 empty] | 2022-11-20
Parent? | Round / Phase | Level Input | Name Input | ID | Name | Predecessor(s) | Planned Duration | Planned Start Date | Planned End Date | Owner(s) | Actual Duration | Actual Start Date | Actual End Date | Status
TRUE |  | 0 | Make awesome WBS template | 1 | Make awesome WBS template |  | 70 | 2020-01-20 | 2020-03-30 | John Shepphard |  | 2020-01-20
TRUE |  | 1 | make formulas | 1.1 | make formulas |  | 5 | 2020-01-25 | 2020-01-30 | Jack O'niell |  | 2020-03-10
FALSE |  | 2 | overly complicated IF() statement | 1.1.1 | overly complicated IF() statement |  | 5 | 2020-01-26 | 2020-01-31 | Catherine Halsey | 13 | 2020-03-12 | 2020-03-25 | Complete
FALSE |  | 2 | indentations for Name column | 1.1.2 | indentations for Name column |  |  |  |  | Bobby Newport
FALSE |  | 2 | elaborate project completion percentage formula | 1.1.3 | elaborate project completion percentage formula |  |  |  |  | Michael Scott
FALSE |  | 1 | lots of formatting | 1.2 | lots of formatting | 1.1 |  |  |  | Ann Perkins
FALSE |  | 1 | ???? | 1.3 | ???? |  |  |  |  | Chuck Testa
FALSE |  | 1 | Profit | 1.4 | Profit | 1.3
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This formula calculates the percentage of non-parent action items (name) that have a status of complete which is used for the project completion percentage

## Work Breakdown Structure New
| Project Inputs |  |  |  | Template Work Breakdown Structure | [5 empty] | Project Completion
|  | 16.67% | [8 empty] | 16.67%
| Project Name: |  | Template
| Project Manager(s) |  | Bob Saget, Rick Astley |  | Project Managers: Bob Saget, Rick Astley | [5 empty] | 2022-11-20
Parent? | Round / Phase | Level Input | Name Input | ID | Name | Predecessor(s) | Planned Duration | Planned Start Date | Planned End Date | Owner(s) | Actual Duration | Actual Start Date | Actual End Date | Status
TRUE |  | 0 | Open Doors at Walker | 1 | Open Doors at Walker |  | 70 | 2020-01-20 | 2020-03-30 | Sanchez |  | 2020-01-20
TRUE |  | 1 | OSPI Application Submitted | 1.1 | OSPI Application Submitted |  | 948 | 2020-01-25 | 2022-08-30 | Becky Pedersen |  | 2020-03-10
FALSE |  | 2 | Complete program statement | 1.1.1 | Complete program statement |  | 5 | 2020-01-26 | 2020-01-31 | Catherine Halsey | 13 | 2020-03-12 | 2020-03-25 | Complete
FALSE |  | 2 | Complete program agreements | 1.1.2 | Complete program agreements |  |  |  |  | Bobby Newport
FALSE |  | 2 | Utilize new let feature | 1.1.3 | Utilize new let feature
TRUE |  | 1 | Staff management | 1.2 | Staff management
TRUE |  | 2 | define program needs | 1.2.1 | define program needs |  |  |  |  | Michael Scott
FALSE |  | 3 | Determine support staff | 1.2.1.1 | Determine support staff |  |  |  |  | Ann Perkins
FALSE |  | 3 | Codify ratios (Case manager) | 1.2.1.2 | Codify ratios (Case manager) | 1.2.1.1 |  |  |  | Chuck Testa
FALSE |  | 1 | Budget | 1.3 | Budget
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This formula calculates the percentage of non-parent action items (name) that have a status of complete which is used for the project completion percentage